## Sheet1
S.No. | Module Name | Bug | Bug Type | Reported On | Locked By | Fixed Date | Fixed By | Remarks | Status
1 | Student | Student-> Filter-> Course and Category DDL width Should be fixed at the time of selection | High | 2019-04-11 | Jata |  |  |  | Open
2 |  | Student-> Filter-> Button name should be Filter instead of Save and also CSS is missing. | High | 2019-04-11 | Jata |  |  |  | Open
3 |  | Student-> Edit Records-> Data should be clear no Cancel and (*) Button on edit screen. | High | 2019-04-11 | Jata |  |  |  | Open
4 |  | Student-> Edit Records-> After image upload, error msg is comming. | High | 2019-04-11 | Jata |  |  |  | Open
5 |  | Student->Add -> DOB calender is missing | High | 2019-04-11 | Jata |  |  |  | Open
6 |  | Student->Add/Edit -> Modal postioning is not fix | High | 2019-04-11 | Jata |  |  |  | Open
7 |  | Student->Add -> Subject Details -> Subjects are not bind | High | 2019-04-11 | Jata |  |  |  | Open
8 |  | Student->Add ->Academic Details -> Course hit name is not correct. | High | 2019-04-11 | Jata |  |  |  | Open
9 |  | Student->Add -> Transport/Hostel -> Maximum DDL are not bind | High | 2019-04-11 | Jata |  |  |  | Open
10 |  | Student->Add -> After Save records data should be clear. | High | 2019-04-11 | Jata |  |  |  | Open
11 |  | Student->Add ->Validation are missing on -Email,Numeric,Length and ZIP code etc | High | 2019-04-11 | Jata |  |  |  | Open
12 |  | Student-> Filter is not working | High | 2019-04-11 | Jata |  |  |  | Open
13 |  | Student-> Export to excel is not working | High | 2019-04-11 | Jata |  |  |  | Open
14 |  | Student->Add-> Designation and Job type data is not bind in ddl. | High | 2019-04-11 | Jata |  |  |  | Open
15 |  | Student->Add-> Login id ,password and conform pass control should be remove. | High | 2019-04-11 | Jata |  |  |  | Open
16 | Employee | Employee->Filter is not working(Grid is not refreshing) | High | 2019-04-11 | Jata |  |  |  | Open
17 |  | Employee-> Export to excel is not working | High | 2019-04-11 | Jata |  |  |  | Open
18 |  | Employee->Add -> Subject Details -> Subjects are not bind | High | 2019-04-11 | Jata |  |  |  | Open
19 |  | Employee->Add ->Validation are missing on -Email,Numeric,Length and ZIP code etc | High | 2019-04-11 | Jata |  |  |  | Open
20 |  | Employee->Edit ->Email id is not bind(Due to edit data is not save). | High | 2019-04-11 | Jata |  |  |  | Open
21 |  | Employee->Edit ->Calender, Save and Update records are save msg are coming back side of the modal | High | 2019-04-11 | Jata |  |  |  | Open
22 |  | Employee->Add/Edit -> Modal postioning is not fix | High | 2019-04-11 | Jata |  |  |  | Open
23 |  | Employee->Add-> Designation and Job type data is not bind in ddl. | High | 2019-04-11 | Jata |  |  |  | Open
24 |  | Employee->Add-> Login id ,password and conform pass control should be remove. | High | 2019-04-11 | Jata |  |  |  | Open
25 |  | Employee->Add-> Login id and password should be send to Student. | High | 2019-04-11 | Jata |  |  |  | Open
26 | Master | Master Management-> Semester sub menu should be remove. | High | 2019-04-11 | Jata |  |  |  | Open
27 |  | Duration-> After save data, Semester data should be clear from ddl | High | 2019-04-11 | Jata |  |  |  | Open
28 |  | Duration-> After save data,Semester Value should be bind instead of id | High | 2019-04-11 | Jata |  |  |  | Open
29 |  | Master Management-> Course Subject mapping Sub menu is not working . | High | 2019-04-11 | Jata | 2019-04-12 | Jata |  | Closed
30 |  | Mapping-> After save data,Semester Value should be bind instead of id | High | 2019-04-11 | Jata |  |  |  | Open
31 |  | Master Management-> Section Sub menu is not working . | High | 2019-04-11 | Jata | 2019-04-12 | Jata |  | Closed
32 |  | Master -> Section ->Section name should be bind instead of id | High | 2019-04-11 | Jata |  |  |  | Open
33 |  | Master -> Section ->No Option to Update section and Semester | High | 2019-04-11 | Jata |  |  |  | Open
34 |  | Master Management-> Course Sub menu is missing . | High | 2019-04-11 | Jata | 2019-04-12 | Jata |  | Closed
35 |  | Master Management-> Activity Sub menu is missing . | High | 2019-04-11 | Jata | 2019-04-12 | Jata |  | Closed
36 |  | Master Management-> Export to Excel is missing from all Master pages. | High | 2019-04-11 | Jata | 2019-04-12 | Jata | Will add on in future | Later
37 |  | Master Management-> Filter is missing from all Master pages. | High | 2019-04-11 | Jata | 2019-04-12 | Jata | Will add on in future | Later
38 | Fee | Fee Type-> Payment Type and Month Name should be bind in grid instead of id. | High | 2019-04-11 | Jata |  |  |  | Open
39 |  | Fee Type-> Month ddl should be enable when Payment Type is Monthly | High | 2019-04-11 | Jata | 2019-04-12 | Jata |  | Closed
40 |  | Fee Details -> Academic Year and Course DDL <select > option is not present. | High | 2019-04-11 | Jata | 2019-04-12 | Jata |  | Closed